## Aug_10_2020
Purpose | Review the data that Vidyod sent over to GE, gets specs
Presuming data is good | Find out how much data is needed to run functional application testing
If the data is not good | Document examples of the problems and determine what the solution is.
If data is good, begin work with Vidyod to reach out to MSP and find time frame for delivering the data to GE.

## Progress
Met with Jeff Brown from GE and received copies of csvs in GE format
Agreed on what the sample data will look like.
reaching out to ravi to discuss long term sustainability of using csv ingestion for NCA
reviewing jeff's data with vidyod and tim
review with vidyod the eta for generating the first samples of ami data.

## Questions
Is it SCE or OMS/MSP team's responsibility to handle the transformation of the data into the GE csv format? It should be on both of their sides.
Technical Documentation from GE providing more details on the workings of NCA
Customer to phase analysis
Customer to transformer analysis
Performance benchmarks and metrics for data consumption
Storage requirements for data. Where is the data stored? How do we load an entire network of data into the system?
Timeframe for updating data, is it incremental?
Reloading the data, and re-running NCA on a new system or test box, does it require all data to be reloaded and stored on the box?
We can provide GE with maybe an A-system of data for 6 months in the csv format, but as far as generating the entire system in the csv format, our concern is the scalability and performance of using this channel due to the resources needed on our side to produce and update the data.
We would like to understand what the end-to-end performance might look like for us to use this application first, otherwise if the performance is a problem to the point that it cannot be regularly used it might be a good idea to start working now on building and testing a better channel.
Is NCA building its own internal DB of AMI data? What type of DB is it?
details on how nca loads in and stores the data
detail on the
| Should column name FeederId and Substation remain consistent? Both named as string or both named as number. | Notes:
| i.e. feederid should be number, and substation name should be string. | Neeraj
timestamp, are the T and ".000+000" fixed values?
is there any need for customer count, priority customer count, and geo coordinates for equipment
jeff brown
chris goman